## Initial Admin Registration
Table STP: Initial Admin Registration Item Pass/Fail Criteria
Test scenarios for this feature of the 1800 Soles Stock Management System.
Test Case ID: |  | 1 | Test Case Description: |  | Initial Admin Registration | Version:
Created By: |  | 1800 Soles Project Team | Reviewed By: |  | QA Reviewer | 1.0
QA Tester’s Log
Tester Name: |  | QA Tester | Date Tested: |  | 04/01/2026 | Test Case (Pass/Fail):
PASS
Prerequisites |  |  | Test Data
1 | System has no existing Admin account. |  | 1 | Last Name, First Name, Middle Name, Suffix(optional), Gender, Phone, Role, Username, Email, Password
Test Scenario: Create initial Admin account using valid data
Step # | Step Details |  | Expected Results |  | Actual Results | Pass/Fail/Not Executed/Suspended
1 | User opens Sign Up and completes all required fields. |  | System validates required fields and password rules. |  | All required fields validated successfully. | PASS
2 | User submits registration. |  | System creates account and assigns role as Admin for initial registration. |  | Initial Admin account created and role assigned as Admin. | PASS
3 | User is redirected to Login. |  | System shows success confirmation and routes user to login. |  | Success message shown and redirected to Login. | PASS
Test Scenario: Block second public admin registration
Step # | Step Details |  | Expected Results |  | Actual Results | Pass/Fail/Not Executed/Suspended
1 | Another user tries to sign up after Admin already exists. |  | System blocks public registration for new Admin and guides to login. |  | Registration blocked after initial admin registration. | PASS
2 | User retries with different email. |  | System still blocks duplicate public admin initialization. |  | Second initialization remains blocked. | PASS
Test Scenario: Validate password confirmation and required fields
Step # | Step Details |  | Expected Results |  | Actual Results | Pass/Fail/Not Executed/Suspended
1 | User leaves required field blank and submits. |  | System highlights missing required fields. |  | Required field validation shown correctly. | PASS
2 | User enters mismatched password and confirm password. |  | System rejects submission due to mismatch. |  | Mismatch warning displayed; account not created. | PASS

## Login1
Table STP: Login Item Pass/Fail Criteria
Test scenarios for this feature of the 1800 Soles Stock Management System.
Test Case ID: |  | 2 | Test Case Description: |  | Login | Version:
Created By: |  | 1800 Soles Project Team | Reviewed By: |  | QA Reviewer | 1.0
QA Tester’s Log
Tester Name: |  | QA Tester | Date Tested: |  | 04/01/2026 | Test Case (Pass/Fail):
PASS
Prerequisites |  |  | Test Data
1 | Registered active account exists. |  | 1 | Username/Email and Password
Test Scenario: Login with valid credentials
Step # | Step Details |  | Expected Results |  | Actual Results | Pass/Fail/Not Executed/Suspended
1 | User enters valid username/email and password. |  | System validates credentials. |  | Credentials validated successfully. | PASS
2 | User clicks Login. |  | System starts session and redirects to Home dashboard. |  | Session created and redirected to Home. | PASS
Test Scenario: Reject invalid credentials
Step # | Step Details |  | Expected Results |  | Actual Results | Pass/Fail/Not Executed/Suspended
1 | User enters wrong password. |  | System denies login and shows error message. |  | Access denied with invalid credentials message. | PASS
Test Scenario: Reject blank fields
Step # | Step Details |  | Expected Results |  | Actual Results | Pass/Fail/Not Executed/Suspended
1 | User clicks Login with empty fields. |  | System blocks submission and highlights required fields. |  | Submission blocked and required prompts displayed. | PASS

## Forgot Password1
Table STP: Forgot Password Item Pass/Fail Criteria
Test scenarios for this feature of the 1800 Soles Stock Management System.
Test Case ID: |  | 3 | Test Case Description: |  | Forgot Password | Version:
Created By: |  | 1800 Soles Project Team | Reviewed By: |  | QA Reviewer | 1.0
QA Tester’s Log
Tester Name: |  | QA Tester | Date Tested: |  | 04/01/2026 | Test Case (Pass/Fail):
PASS
Prerequisites |  |  | Test Data
1 | User account has registered email and SMTP is configured. |  | 1 | Registered Email Address
Test Scenario: Send reset link to registered email
Step # | Step Details |  | Expected Results |  | Actual Results | Pass/Fail/Not Executed/Suspended
1 | User opens Forgot Password and enters registered email. |  | System accepts request and generates reset token. |  | Reset token generated successfully. | PASS
2 | User submits request. |  | System sends password reset link to email and shows confirmation. |  | Reset email sent and confirmation displayed. | PASS
Test Scenario: Reject unregistered email
Step # | Step Details |  | Expected Results |  | Actual Results | Pass/Fail/Not Executed/Suspended
1 | User enters email not found in system. |  | System returns safe error/notice and does not expose account details. |  | Request handled safely; no account leak. | PASS
Test Scenario: Reset password using valid token
Step # | Step Details |  | Expected Results |  | Actual Results | Pass/Fail/Not Executed/Suspended
1 | User opens reset link and enters new password. |  | System validates token and updates password hash. |  | Password updated and token marked used. | PASS
2 | User returns to Login and signs in with new password. |  | System authenticates with updated credentials. |  | Login successful with new password. | PASS

## Dashboard (Home)1
Table STP: Dashboard (Home) Item Pass/Fail Criteria
Test scenarios for this feature of the 1800 Soles Stock Management System.
Test Case ID: |  | 4 | Test Case Description: |  | Dashboard (Home) | Version:
Created By: |  | 1800 Soles Project Team | Reviewed By: |  | QA Reviewer | 1.0
QA Tester’s Log
Tester Name: |  | QA Tester | Date Tested: |  | 04/01/2026 | Test Case (Pass/Fail):
PASS
Prerequisites |  |  | Test Data
1 | User is logged in and inventory has records. |  | 1 | Inventory summaries and latest activity logs
Test Scenario: Display summary cards
Step # | Step Details |  | Expected Results |  | Actual Results | Pass/Fail/Not Executed/Suspended
1 | User opens Home dashboard. |  | System shows Total Items, In Stock, Waiting Stock, and Activity counters. |  | All summary cards displayed correctly. | PASS
Test Scenario: Display recent activity list
Step # | Step Details |  | Expected Results |  | Actual Results | Pass/Fail/Not Executed/Suspended
1 | User checks Recent Activity section. |  | System shows latest 5 inventory actions with formatted labels. |  | Recent activity rendered with latest actions. | PASS
Test Scenario: Display stock status summary as text
Step # | Step Details |  | Expected Results |  | Actual Results | Pass/Fail/Not Executed/Suspended
1 | User views stock status summary area. |  | System displays textual stock status summary for In Stock and Waiting Stock. |  | Textual stock summary displayed correctly. | PASS

## Inventory Viewing1
Table STP: Inventory Viewing Item Pass/Fail Criteria
Test scenarios for this feature of the 1800 Soles Stock Management System.
Test Case ID: |  | 5 | Test Case Description: |  | Inventory Viewing | Version:
Created By: |  | 1800 Soles Project Team | Reviewed By: |  | QA Reviewer | 1.0
QA Tester’s Log
Tester Name: |  | QA Tester | Date Tested: |  | 04/01/2026 | Test Case (Pass/Fail):
PASS
Prerequisites |  |  | Test Data
1 | User is logged in and inventory contains items. |  | 1 | Inventory list with available quantity and status
Test Scenario: View inventory table columns
Step # | Step Details |  | Expected Results |  | Actual Results | Pass/Fail/Not Executed/Suspended
1 | User opens Inventory tab. |  | System displays item name, available qty, last movement, status, and item details column. |  | Table columns rendered correctly. | PASS
Test Scenario: Paginate inventory table
Step # | Step Details |  | Expected Results |  | Actual Results | Pass/Fail/Not Executed/Suspended
1 | User navigates next and previous page. |  | System shows maximum 10 rows per page with working pagination controls. |  | Pagination works with 10-row page size. | PASS
Test Scenario: Open item details from table
Step # | Step Details |  | Expected Results |  | Actual Results | Pass/Fail/Not Executed/Suspended
1 | User clicks Details on an item row. |  | Item Details modal opens with pair records and summary. |  | Item Details modal opened successfully. | PASS

## Search Item
Table STP: Search Item Item Pass/Fail Criteria
Test scenarios for this feature of the 1800 Soles Stock Management System.
Test Case ID: |  | 6 | Test Case Description: |  | Search Item | Version:
Created By: |  | 1800 Soles Project Team | Reviewed By: |  | QA Reviewer | 1.0
QA Tester’s Log
Tester Name: |  | QA Tester | Date Tested: |  | 04/01/2026 | Test Case (Pass/Fail):
PASS
Prerequisites |  |  | Test Data
1 | User is on Inventory page with existing items. |  | 1 | Keyword by item name, brand, colorway, or SKU
Test Scenario: Search by SKU
Step # | Step Details |  | Expected Results |  | Actual Results | Pass/Fail/Not Executed/Suspended
1 | User enters SKU keyword in search input. |  | System filters and displays matching item rows. |  | SKU filter returned expected result. | PASS
Test Scenario: Search by item name/brand/colorway
Step # | Step Details |  | Expected Results |  | Actual Results | Pass/Fail/Not Executed/Suspended
1 | User enters name or brand keyword. |  | System returns matching records only. |  | Keyword search returned correct rows. | PASS
Test Scenario: Clear search
Step # | Step Details |  | Expected Results |  | Actual Results | Pass/Fail/Not Executed/Suspended
1 | User clears search field. |  | System restores full inventory list. |  | Full list restored after clearing search. | PASS

## Add Item (New Product)
Table STP: Add Item (New Product) Item Pass/Fail Criteria
Test scenarios for this feature of the 1800 Soles Stock Management System.
Test Case ID: |  | 7 | Test Case Description: |  | Add Item (New Product) | Version:
Created By: |  | 1800 Soles Project Team | Reviewed By: |  | QA Reviewer | 1.0
QA Tester’s Log
Tester Name: |  | QA Tester | Date Tested: |  | 04/01/2026 | Test Case (Pass/Fail):
PASS
Prerequisites |  |  | Test Data
1 | User is logged in and Inventory page is accessible. |  | 1 | Item Name, SKU, Colorway, Brand, Target Quantity
Test Scenario: Create new item with valid details
Step # | Step Details |  | Expected Results |  | Actual Results | Pass/Fail/Not Executed/Suspended
1 | User opens Add Item modal and enters valid data. |  | System validates required fields. |  | Validation passed for required fields. | PASS
2 | User clicks Create Item. |  | System creates item record and shows success toast. |  | Item created and success toast displayed. | PASS
Test Scenario: Prevent duplicate item entry
Step # | Step Details |  | Expected Results |  | Actual Results | Pass/Fail/Not Executed/Suspended
1 | User submits item with duplicate identifying values. |  | System rejects duplicate and shows error message. |  | Duplicate item blocked correctly. | PASS
Test Scenario: Record Add Item in activity log
Step # | Step Details |  | Expected Results |  | Actual Results | Pass/Fail/Not Executed/Suspended
1 | After successful add, user opens Activity Log. |  | System records ADD_ITEM action with timestamp and details. |  | ADD_ITEM entry is present in activity log. | PASS

## Stock In (Add Pair Record)
Table STP: Stock In (Add Pair Record) Item Pass/Fail Criteria
Test scenarios for this feature of the 1800 Soles Stock Management System.
Test Case ID: |  | 8 | Test Case Description: |  | Stock In (Add Pair Record) | Version:
Created By: |  | 1800 Soles Project Team | Reviewed By: |  | QA Reviewer | 1.0
QA Tester’s Log
Tester Name: |  | QA Tester | Date Tested: |  | 04/01/2026 | Test Case (Pass/Fail):
PASS
Prerequisites |  |  | Test Data
1 | Existing item is available in Inventory. |  | 1 | Pair code, Size, Gender, Condition, Cost Price, Selling Price
Test Scenario: Add pair under existing item
Step # | Step Details |  | Expected Results |  | Actual Results | Pass/Fail/Not Executed/Suspended
1 | User opens Item Details then Stock In section. |  | System accepts valid pair data and saves pair record. |  | Pair created successfully under selected item. | PASS
2 | User submits Stock In. |  | Available quantity updates and item status recalculates. |  | Quantity and status updated correctly. | PASS
Test Scenario: Validate stock-in fields
Step # | Step Details |  | Expected Results |  | Actual Results | Pass/Fail/Not Executed/Suspended
1 | User enters invalid size/price and submits. |  | System blocks submission and displays validation messages. |  | Invalid stock-in data rejected. | PASS
Test Scenario: Record Stock In in activity log
Step # | Step Details |  | Expected Results |  | Actual Results | Pass/Fail/Not Executed/Suspended
1 | User checks Activity Log after stock in. |  | System records STOCK_IN action with item/pair details. |  | STOCK_IN entry logged successfully. | PASS

## Mark Sold1
Table STP: Mark Sold Item Pass/Fail Criteria
Test scenarios for this feature of the 1800 Soles Stock Management System.
Test Case ID: |  | 9 | Test Case Description: |  | Mark Sold | Version:
Created By: |  | 1800 Soles Project Team | Reviewed By: |  | QA Reviewer | 1.0
QA Tester’s Log
Tester Name: |  | QA Tester | Date Tested: |  | 04/01/2026 | Test Case (Pass/Fail):
PASS
Prerequisites |  |  | Test Data
1 | Item has available pair records. |  | 1 | Selected pair marked as Available
Test Scenario: Mark available pair as sold
Step # | Step Details |  | Expected Results |  | Actual Results | Pass/Fail/Not Executed/Suspended
1 | User clicks Mark Sold on an available pair. |  | System confirms action and sets pair as Sold. |  | Pair status changed to Sold. | PASS
2 | System updates inventory values. |  | Available quantity decreases and sold date is recorded. |  | Qty decreased and sold date shown. | PASS
Test Scenario: Enforce waiting stock threshold
Step # | Step Details |  | Expected Results |  | Actual Results | Pass/Fail/Not Executed/Suspended
1 | Available qty reaches 25 pct or below target qty. |  | System disables/blocks further Mark Sold actions. |  | Mark Sold blocked at threshold condition. | PASS
Test Scenario: Record Mark Sold in activity log
Step # | Step Details |  | Expected Results |  | Actual Results | Pass/Fail/Not Executed/Suspended
1 | User checks Activity Log. |  | System records MARK_SOLD with quantity and sold price. |  | MARK_SOLD action logged correctly. | PASS

## Edit Product Details
Table STP: Edit Product Details Item Pass/Fail Criteria
Test scenarios for this feature of the 1800 Soles Stock Management System.
Test Case ID: |  | 10 | Test Case Description: |  | Edit Product Details | Version:
Created By: |  | 1800 Soles Project Team | Reviewed By: |  | QA Reviewer | 1.0
QA Tester’s Log
Tester Name: |  | QA Tester | Date Tested: |  | 04/01/2026 | Test Case (Pass/Fail):
PASS
Prerequisites |  |  | Test Data
1 | Existing item and pair data are available. |  | 1 | Updated item and pair details
Test Scenario: Edit item details
Step # | Step Details |  | Expected Results |  | Actual Results | Pass/Fail/Not Executed/Suspended
1 | User opens Edit Item modal from Item Details. |  | System loads existing values for editing. |  | Edit form auto-populated correctly. | PASS
2 | User saves updated item details. |  | System validates and updates item record. |  | Item details updated successfully. | PASS
Test Scenario: Edit pair details
Step # | Step Details |  | Expected Results |  | Actual Results | Pass/Fail/Not Executed/Suspended
1 | User opens Edit Pair from available row. |  | System loads pair values in modal. |  | Pair edit modal auto-populated correctly. | PASS
2 | User saves pair changes. |  | System updates pair data and refreshes table. |  | Pair details updated and table refreshed. | PASS
Test Scenario: Log edit actions
Step # | Step Details |  | Expected Results |  | Actual Results | Pass/Fail/Not Executed/Suspended
1 | User checks Activity Log after edits. |  | System records edit actions with timestamp. |  | Edit actions logged successfully. | PASS

## Archive Item
Table STP: Archive Item Item Pass/Fail Criteria
Test scenarios for this feature of the 1800 Soles Stock Management System.
Test Case ID: |  | 11 | Test Case Description: |  | Archive Item | Version:
Created By: |  | 1800 Soles Project Team | Reviewed By: |  | QA Reviewer | 1.0
QA Tester’s Log
Tester Name: |  | QA Tester | Date Tested: |  | 04/01/2026 | Test Case (Pass/Fail):
PASS
Prerequisites |  |  | Test Data
1 | Inventory has active items. |  | 1 | Selected active item
Test Scenario: Archive active item
Step # | Step Details |  | Expected Results |  | Actual Results | Pass/Fail/Not Executed/Suspended
1 | User archives an active item. |  | System sets item_status to inactive and removes item from active inventory list. |  | Item archived and hidden from active list. | PASS
Test Scenario: Show archived item in Archive tab
Step # | Step Details |  | Expected Results |  | Actual Results | Pass/Fail/Not Executed/Suspended
1 | User opens Archive tab. |  | Archived item appears with archive action controls. |  | Archived item listed in Archive tab. | PASS
Test Scenario: Log archive action
Step # | Step Details |  | Expected Results |  | Actual Results | Pass/Fail/Not Executed/Suspended
1 | User checks Activity Log. |  | System records ARCHIVE action with timestamp and item details. |  | ARCHIVE action logged correctly. | PASS

## Restore Archived Item
Table STP: Restore Archived Item Item Pass/Fail Criteria
Test scenarios for this feature of the 1800 Soles Stock Management System.
Test Case ID: |  | 12 | Test Case Description: |  | Restore Archived Item | Version:
Created By: |  | 1800 Soles Project Team | Reviewed By: |  | QA Reviewer | 1.0
QA Tester’s Log
Tester Name: |  | QA Tester | Date Tested: |  | 04/01/2026 | Test Case (Pass/Fail):
PASS
Prerequisites |  |  | Test Data
1 | At least one item is archived. |  | 1 | Archived item selected in Archive tab
Test Scenario: Restore archived item
Step # | Step Details |  | Expected Results |  | Actual Results | Pass/Fail/Not Executed/Suspended
1 | User clicks Restore on archived item. |  | System sets item_status back to active. |  | Item restored successfully. | PASS
Test Scenario: Return item to active inventory list
Step # | Step Details |  | Expected Results |  | Actual Results | Pass/Fail/Not Executed/Suspended
1 | User opens Inventory tab. |  | Restored item appears again in inventory table. |  | Restored item visible in active inventory. | PASS
Test Scenario: Log restore action
Step # | Step Details |  | Expected Results |  | Actual Results | Pass/Fail/Not Executed/Suspended
1 | User checks Activity Log. |  | System records RESTORE action with timestamp. |  | RESTORE action logged correctly. | PASS

## Delete Product Permanently
Table STP: Delete Product Permanently Item Pass/Fail Criteria
Test scenarios for this feature of the 1800 Soles Stock Management System.
Test Case ID: |  | 13 | Test Case Description: |  | Delete Product Permanently | Version:
Created By: |  | 1800 Soles Project Team | Reviewed By: |  | QA Reviewer | 1.0
QA Tester’s Log
Tester Name: |  | QA Tester | Date Tested: |  | 04/01/2026 | Test Case (Pass/Fail):
PASS
Prerequisites |  |  | Test Data
1 | Item is archived and user has Admin privilege. |  | 1 | Archived item and Admin password confirmation
Test Scenario: Delete permanently from Archive tab
Step # | Step Details |  | Expected Results |  | Actual Results | Pass/Fail/Not Executed/Suspended
1 | Admin clicks Delete Permanently for archived item. |  | System asks for admin password confirmation. |  | Confirmation prompt displayed correctly. | PASS
2 | Admin enters valid password and confirms. |  | System permanently removes record. |  | Archived item deleted permanently. | PASS
Test Scenario: Prevent permanent delete without archive state
Step # | Step Details |  | Expected Results |  | Actual Results | Pass/Fail/Not Executed/Suspended
1 | User tries delete on non-archived item path. |  | System blocks operation outside archived flow. |  | Delete blocked unless item is archived. | PASS
Test Scenario: Log permanent delete action
Step # | Step Details |  | Expected Results |  | Actual Results | Pass/Fail/Not Executed/Suspended
1 | User checks Activity Log. |  | System records DELETE_PERMANENT with timestamp. |  | Permanent delete action logged. | PASS

## Activity Log1
Table STP: Activity Log Item Pass/Fail Criteria
Test scenarios for this feature of the 1800 Soles Stock Management System.
Test Case ID: |  | 14 | Test Case Description: |  | Activity Log | Version:
Created By: |  | 1800 Soles Project Team | Reviewed By: |  | QA Reviewer | 1.0
QA Tester’s Log
Tester Name: |  | QA Tester | Date Tested: |  | 04/01/2026 | Test Case (Pass/Fail):
PASS
Prerequisites |  |  | Test Data
1 | Inventory and settings actions have been performed. |  | 1 | Logged actions (ADD_ITEM, STOCK_IN, MARK_SOLD, ARCHIVE, RESTORE, DELETE_PERMANENT)
Test Scenario: Display activity log records
Step # | Step Details |  | Expected Results |  | Actual Results | Pass/Fail/Not Executed/Suspended
1 | User opens Activity Log tab. |  | System lists actions with date/time, item, action, quantity, and sold price when applicable. |  | Activity log displayed with complete columns. | PASS
Test Scenario: Paginate activity log
Step # | Step Details |  | Expected Results |  | Actual Results | Pass/Fail/Not Executed/Suspended
1 | User navigates activity log pages. |  | System shows max 10 rows per page with next/previous controls. |  | Pagination works with 10-row limit. | PASS
Test Scenario: Format action labels and colors
Step # | Step Details |  | Expected Results |  | Actual Results | Pass/Fail/Not Executed/Suspended
1 | User reviews action labels. |  | MARK_SOLD, STOCK_IN, and ADD_ITEM use distinct colors; other actions use neutral style. |  | Action formatting is consistent and readable. | PASS

## Analytics1
Table STP: Analytics Item Pass/Fail Criteria
Test scenarios for this feature of the 1800 Soles Stock Management System.
Test Case ID: |  | 15 | Test Case Description: |  | Analytics | Version:
Created By: |  | 1800 Soles Project Team | Reviewed By: |  | QA Reviewer | 1.0
QA Tester’s Log
Tester Name: |  | QA Tester | Date Tested: |  | 04/01/2026 | Test Case (Pass/Fail):
PASS
Prerequisites |  |  | Test Data
1 | Inventory has item and pair transactions. |  | 1 | Summary metrics and chart datasets
Test Scenario: Load analytics metrics
Step # | Step Details |  | Expected Results |  | Actual Results | Pass/Fail/Not Executed/Suspended
1 | User opens Analytics page. |  | System displays summary cards (sales, profit, stock value equivalent metric) and computed figures. |  | Summary metrics loaded correctly. | PASS
Test Scenario: Render interactive charts
Step # | Step Details |  | Expected Results |  | Actual Results | Pass/Fail/Not Executed/Suspended
1 | User hovers chart points/bars. |  | System shows tooltips and interactive responses for trend/distribution charts. |  | Charts render and hover tooltips work. | PASS
Test Scenario: Reflect latest inventory changes
Step # | Step Details |  | Expected Results |  | Actual Results | Pass/Fail/Not Executed/Suspended
1 | User performs inventory transactions then refreshes Analytics. |  | Computed values and datasets update based on latest records. |  | Analytics values refreshed from latest data. | PASS

## Download CSV File
Table STP: Download CSV File Item Pass/Fail Criteria
Test scenarios for this feature of the 1800 Soles Stock Management System.
Test Case ID: |  | 16 | Test Case Description: |  | Download CSV File | Version:
Created By: |  | 1800 Soles Project Team | Reviewed By: |  | QA Reviewer | 1.0
QA Tester’s Log
Tester Name: |  | QA Tester | Date Tested: |  | 04/01/2026 | Test Case (Pass/Fail):
PASS
Prerequisites |  |  | Test Data
1 | Inventory contains records and user is logged in. |  | 1 | Current inventory dataset
Test Scenario: Download inventory CSV
Step # | Step Details |  | Expected Results |  | Actual Results | Pass/Fail/Not Executed/Suspended
1 | User clicks Download CSV File. |  | System generates and downloads CSV file. |  | CSV downloaded successfully. | PASS
Test Scenario: Validate CSV content
Step # | Step Details |  | Expected Results |  | Actual Results | Pass/Fail/Not Executed/Suspended
1 | User opens downloaded CSV. |  | File contains current inventory fields and values matching system data. |  | CSV content matches on-screen inventory. | PASS
Test Scenario: Validate CSV update after edits
Step # | Step Details |  | Expected Results |  | Actual Results | Pass/Fail/Not Executed/Suspended
1 | User updates inventory then downloads CSV again. |  | New export reflects latest modifications. |  | CSV includes latest inventory changes. | PASS

## Settings (Profile Update)1
Table STP: Settings (Profile Update) Item Pass/Fail Criteria
Test scenarios for this feature of the 1800 Soles Stock Management System.
Test Case ID: |  | 17 | Test Case Description: |  | Settings (Profile Update) | Version:
Created By: |  | 1800 Soles Project Team | Reviewed By: |  | QA Reviewer | 1.0
QA Tester’s Log
Tester Name: |  | QA Tester | Date Tested: |  | 04/01/2026 | Test Case (Pass/Fail):
PASS
Prerequisites |  |  | Test Data
1 | User is authenticated. |  | 1 | Last Name, First Name, Middle Name, Suffix(optional), Email, Username, Phone, Gender
Test Scenario: Update editable profile fields
Step # | Step Details |  | Expected Results |  | Actual Results | Pass/Fail/Not Executed/Suspended
1 | User edits allowed profile fields in Settings. |  | System validates input and saves updates. |  | Profile updates saved successfully. | PASS
Test Scenario: Enforce readonly fields
Step # | Step Details |  | Expected Results |  | Actual Results | Pass/Fail/Not Executed/Suspended
1 | User attempts to modify readonly fields (if configured). |  | System keeps protected fields unchanged. |  | Readonly fields remain unchanged. | PASS
Test Scenario: Log profile update action
Step # | Step Details |  | Expected Results |  | Actual Results | Pass/Fail/Not Executed/Suspended
1 | User checks Activity Log after saving profile. |  | System records profile update action. |  | Profile update logged successfully. | PASS

## Change Password1
Table STP: Change Password Item Pass/Fail Criteria
Test scenarios for this feature of the 1800 Soles Stock Management System.
Test Case ID: |  | 18 | Test Case Description: |  | Change Password | Version:
Created By: |  | 1800 Soles Project Team | Reviewed By: |  | QA Reviewer | 1.0
QA Tester’s Log
Tester Name: |  | QA Tester | Date Tested: |  | 04/01/2026 | Test Case (Pass/Fail):
PASS
Prerequisites |  |  | Test Data
1 | User is authenticated and knows current password. |  | 1 | Current Password, New Password, Confirm New Password
Test Scenario: Change password with valid input
Step # | Step Details |  | Expected Results |  | Actual Results | Pass/Fail/Not Executed/Suspended
1 | User enters correct current password and valid new password. |  | System verifies current password and updates password hash. |  | Password changed successfully. | PASS
2 | User logs in using new password. |  | System authenticates with new password. |  | Login successful using new password. | PASS
Test Scenario: Reject wrong current password
Step # | Step Details |  | Expected Results |  | Actual Results | Pass/Fail/Not Executed/Suspended
1 | User enters incorrect current password. |  | System rejects update and shows error. |  | Password change blocked for wrong current password. | PASS
Test Scenario: Reject invalid new password or mismatch
Step # | Step Details |  | Expected Results |  | Actual Results | Pass/Fail/Not Executed/Suspended
1 | User enters weak or mismatched new password. |  | System enforces password rules and confirmation match. |  | Invalid new password blocked. | PASS

## Staff Account Creation
Table STP: Staff Account Creation Item Pass/Fail Criteria
Test scenarios for this feature of the 1800 Soles Stock Management System.
Test Case ID: |  | 19 | Test Case Description: |  | Staff Account Creation | Version:
Created By: |  | 1800 Soles Project Team | Reviewed By: |  | QA Reviewer | 1.0
QA Tester’s Log
Tester Name: |  | QA Tester | Date Tested: |  | 04/01/2026 | Test Case (Pass/Fail):
PASS
Prerequisites |  |  | Test Data
1 | Admin is logged in and opens Staff Management tab in Settings. |  | 1 | Staff profile data: role=Staff, name fields, gender, phone, username, email
Test Scenario: Create staff account as Admin
Step # | Step Details |  | Expected Results |  | Actual Results | Pass/Fail/Not Executed/Suspended
1 | Admin enters complete staff details and submits Create Staff. |  | System validates required fields and creates staff account. |  | Staff account created successfully. | PASS
Test Scenario: Prevent duplicate username/email
Step # | Step Details |  | Expected Results |  | Actual Results | Pass/Fail/Not Executed/Suspended
1 | Admin tries to create staff with existing username or email. |  | System rejects duplicate account credentials. |  | Duplicate username/email blocked. | PASS
Test Scenario: Record staff creation in activity log
Step # | Step Details |  | Expected Results |  | Actual Results | Pass/Fail/Not Executed/Suspended
1 | Admin checks Activity Log. |  | System records CREATE_STAFF action. |  | CREATE_STAFF action logged successfully. | PASS

## Deactivate Staff Account
Table STP: Deactivate Staff Account Item Pass/Fail Criteria
Test scenarios for this feature of the 1800 Soles Stock Management System.
Test Case ID: |  | 20 | Test Case Description: |  | Deactivate Staff Account | Version:
Created By: |  | 1800 Soles Project Team | Reviewed By: |  | QA Reviewer | 1.0
QA Tester’s Log
Tester Name: |  | QA Tester | Date Tested: |  | 04/01/2026 | Test Case (Pass/Fail):
PASS
Prerequisites |  |  | Test Data
1 | Admin is logged in and at least one active staff account exists. |  | 1 | Selected Staff Account + current Admin password
Test Scenario: Deactivate staff with admin verification
Step # | Step Details |  | Expected Results |  | Actual Results | Pass/Fail/Not Executed/Suspended
1 | Admin clicks Deactivate and enters current admin password. |  | System verifies admin password before status change. |  | Admin password verified successfully. | PASS
2 | Admin confirms deactivation. |  | System sets staff is_active to 0 and records date_terminated. |  | Staff account deactivated successfully. | PASS
Test Scenario: Block login for deactivated staff
Step # | Step Details |  | Expected Results |  | Actual Results | Pass/Fail/Not Executed/Suspended
1 | Deactivated staff attempts login. |  | System denies authentication for inactive account. |  | Login blocked for deactivated staff. | PASS
Test Scenario: Log deactivation action
Step # | Step Details |  | Expected Results |  | Actual Results | Pass/Fail/Not Executed/Suspended
1 | Admin checks Activity Log. |  | System records DEACTIVATE_STAFF action. |  | DEACTIVATE_STAFF action logged. | PASS

## Send Reset Link
Table STP: Send Reset Link Item Pass/Fail Criteria
Test scenarios for this feature of the 1800 Soles Stock Management System.
Test Case ID: |  | 21 | Test Case Description: |  | Send Reset Link | Version:
Created By: |  | 1800 Soles Project Team | Reviewed By: |  | QA Reviewer | 1.0
QA Tester’s Log
Tester Name: |  | QA Tester | Date Tested: |  | 04/01/2026 | Test Case (Pass/Fail):
PASS
Prerequisites |  |  | Test Data
1 | Admin is logged in, staff account exists, and SMTP is configured. |  | 1 | Selected staff email + current Admin password
Test Scenario: Send staff password reset link
Step # | Step Details |  | Expected Results |  | Actual Results | Pass/Fail/Not Executed/Suspended
1 | Admin clicks Send Reset Link for selected staff and enters admin password. |  | System verifies admin password then sends reset link email. |  | Reset link sent successfully to staff email. | PASS
Test Scenario: Reject wrong admin password
Step # | Step Details |  | Expected Results |  | Actual Results | Pass/Fail/Not Executed/Suspended
1 | Admin enters incorrect password during send reset action. |  | System blocks send operation and displays error. |  | Reset link not sent with invalid admin password. | PASS
Test Scenario: Record reset-link action
Step # | Step Details |  | Expected Results |  | Actual Results | Pass/Fail/Not Executed/Suspended
1 | Admin checks Activity Log. |  | System records SEND_STAFF_RESET_LINK action. |  | Send reset link action logged. | PASS

## Logout1
Table STP: Logout Item Pass/Fail Criteria
Test scenarios for this feature of the 1800 Soles Stock Management System.
Test Case ID: |  | 22 | Test Case Description: |  | Logout | Version:
Created By: |  | 1800 Soles Project Team | Reviewed By: |  | QA Reviewer | 1.0
QA Tester’s Log
Tester Name: |  | QA Tester | Date Tested: |  | 04/01/2026 | Test Case (Pass/Fail):
PASS
Prerequisites |  |  | Test Data
1 | User is logged in with active session. |  | 1 | Active authenticated session
Test Scenario: Logout from sidebar button
Step # | Step Details |  | Expected Results |  | Actual Results | Pass/Fail/Not Executed/Suspended
1 | User clicks Logout button. |  | System destroys current session and redirects to login page. |  | Session destroyed and redirected to login. | PASS
Test Scenario: Block access to protected pages after logout
Step # | Step Details |  | Expected Results |  | Actual Results | Pass/Fail/Not Executed/Suspended
1 | User tries opening protected URL after logout. |  | System requires authentication and redirects to login. |  | Protected pages blocked after logout. | PASS
Test Scenario: Record logout in activity log
Step # | Step Details |  | Expected Results |  | Actual Results | Pass/Fail/Not Executed/Suspended
1 | User logs in again and checks Activity Log. |  | System records LOGOUT action with timestamp. |  | LOGOUT entry exists in activity log. | PASS